## Pembagian Modul (hidden)
Pembagian Modul Untuk Mapping Table
No | Modul | Table | PIC | Status | Due Date | Endate | Status Table | Name | Status
1 | Common | Tbl_Parameter | Mayer | Closed | 2011-06-24 |  | Closed | Mayer | Open
|  | Tbl_Company |  | Closed | 2011-06-24 |  | Closed | Whidia | In Progress
|  | Tbl_Org_Structure |  | Closed | 2011-06-24 |  | In Progress | Alex Sandro | Closed
|  | Tbl_In_Person |  | Closed | 2011-06-24 |  | Closed | Fitriani | Dropped
|  | Tbl_Ex_Person |  | Closed | 2011-06-24 |  | Closed | Togu | Pending
|  | Tbl_Location |  | Closed | 2011-06-27 | 2011-06-27 | Pending
|  | Tbl_Vehicle_Type |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Vehicle_List |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Driver_Operator |  | Closed | 2011-06-24 |  | Closed
|  | Login |  | Dropped | 2011-06-24 |  | Dropped
|  | Tbl_TypeLocation |  | Closed |  | 2011-06-27 | Pending
2 | Eksplorasi | Tbl_Drilling | Alex Sandro | Closed | 2011-06-24 |  | Closed
|  | Tbl_Drilling_Dtl |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Drilling_Hole_Reconcile |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Geodas_Lithology |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Sample_Analysis |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Parameter_Eksplorasi |  | Closed | 2011-06-24 |  | Closed
3 | Produksi dan view untuk report | Tbl_Dump_Rotation | Whidia | Closed | 2011-06-24 |  | Closed
|  | Tbl_Dump_Rotation_Dtl_Veh |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Dump_Rotation_Dtl_Rot |  | Dropped |  |  | Dropped
|  | Tbl_Dump_Truck_Hauling |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Crusher |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Record_Crusher |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Time_Sheet_Equipment |  | Closed | 2011-06-24 |  | Closed
|  | View |  | Open |  |  | Open
4 | Logistik | Tbl_Part_Group | Fitriani | Closed | 2011-06-24 |  | Closed
|  | Tbl_Storage |  | Closed | 2011-06-27 | 2011-06-27 | Closed
|  | Tbl_Part |  | Closed | 2011-06-27 | 2011-06-27 | Closed
|  | Tbl_Part_Location |  | Closed | 2011-06-24 |  | Pending
|  | Tbl_Daily_Stock |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Part_Request |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Part_Request_Dtl |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Part_Order |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Part_Order_Dtl |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Stock_Opname_Balance |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Fuel_Tanker |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Fuel_Compsution |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Type_Storage |  | Closed | 2011-06-24 | 2011-06-27 | Pending
5 | Setting environment | Setting Server | Togu | Closed | 2011-06-24 |  | Closed
|  | Kostumisasi Framework SI Del |  | In Progress |  |  | In Progress
|  | Setting User |  | In Progress | 2011-06-27 |  | Closed

## Tabel
Daftar Tabel |  | Total Tabel | Master | 5 |  | Jenis Tabel | Master | Referensi | Transaksi | Total
Data Architect : Kelompok 06 |  |  | Referensi | 1 |  | Jumlah | 5 | 1 | 2 | 8
DBA : Daud Manurung |  |  | Transaksi | 2
8
No | Modul | Nama | Jenis | Deskripsi Isi | Status
[5 empty] | Designed * |  | Created |  | Modified
[5 empty] | Plan | Real | Plan | Real | Plan
1 | Registrasi | t_user | Master |  | - | - | 2020-05-01 | - | -
2 | Login | t_user | Master |  |  |  | 2020-05-01 | - | -
3 | Melihat Pilihan | t_kandidat | master |  | - | - | 2020-05-01 | - | -
4 | Melakukan Voting | m_voting | transaksi |  | - | - | 2020-05-01 | - | -
5 | Mengirim email | hasil_voting | referensi |  | - | - | 2020-05-01 | - | -
6 | Mencetak hasil voting | hasil_voting | referensi |  | - | - | 2020-05-01 | - | -

## Pembagian Form (hidden)
Pembagian Modul Untuk Pembuatan Form dan Validasi
No | Modul | Form | PIC | Validasi | Status | Due Date | Name | Status
1 | Common | Tbl_Parameter | Mayer | Open | Closed |  | Mayer | Open
|  | Tbl_Company |  | Open | Closed |  | Whidia | In Progress
|  | Tbl_Org_Structure |  | Open | Closed |  | Alex Sandro | Closed
|  | Tbl_In_Person |  | Open | Closed |  | Fitriani | Dropped
|  | Tbl_Ex_Person |  | Open | Closed |  | Togu | Pending
|  | Tbl_Location |  | Open | In Progress
|  | Tbl_Vehicle_Type |  | Open | Closed
|  | Tbl_Vehicle_List |  | Open | Closed
|  | Tbl_Driver_Operator |  | Open | Closed
|  | Login |  | Dropped | Dropped
|  | Tbl_TypeLocation |  | Pending | Dropped
2 | Eksplorasi | Tbl_Drilling | Alex Sandro | Open | Closed
|  | Tbl_Drilling_Dtl |  | Open | Closed
|  | Tbl_Drilling_Hole_Reconcile |  | Open | Closed
|  | Tbl_Geodas_Lithology |  | Open | Closed
|  | Tbl_Sample_Analysis |  | Open | Closed
|  | Tbl_Parameter_Eksplorasi |  | Open | Closed
3 | Produksi dan view untuk report | Tbl_Dump_Rotation | Whidia | Open | Closed
|  | Tbl_Dump_Rotation_Dtl_Veh |  | Open | Closed
|  | Tbl_Dump_Rotation_Dtl_Rot |  | Open | Closed
|  | Tbl_Dump_Truck_Hauling |  | Open | Closed
|  | Tbl_Crusher |  | Open | Closed
|  | Tbl_Record_Crusher |  | Open | Closed
|  | Tbl_Time_Sheet_Equipment |  | Open | Closed
|  | View |  | Open | Open
4 | Logistik | Tbl_Part_Group | Fitriani | Open | Closed
|  | Tbl_Storage |  | Open | In Progress
|  | Tbl_Part |  | Open | Closed
|  | Tbl_Part_Location |  | Open | Closed
|  | Tbl_Daily_Stock |  | Open | Closed
|  | Tbl_Part_Request |  | Open | Closed
|  | Tbl_Part_Request_Dtl |  | Open | Closed
|  | Tbl_Part_Order |  | Open | Closed
|  | Tbl_Part_Order_Dtl |  | Open | Closed
|  | Tbl_Stock_Opname_Balance |  | Open | Closed
|  | Tbl_Fuel_Tanker |  | Open | Closed
|  | Tbl_Fuel_Compsution |  | Open | Closed
|  | Tbl_Type_Storage |  | Dropped | Dropped
5 | Setting environment | Setting Server | Togu | Closed | Closed
|  | Kostumisasi Framework SI Del |  | In Progress | In Progress
|  | Setting User |  | Closed | Closed

## Trigger dan View (hidden)
Sampai saat ini belum ada.

## Tabel Detail (hidden)
1. Daftar Tabel Framework SIDEL
No. | Jenis | Nama | Jumlah
1 | Master | sys_m_application | 5
sys_m_imap
sys_m_role
sys_m_table
sys_m_user
2 | Detail | sys_d_function | 3
sys_d_profile
sys_d_unit
3 | Referensi | sys_r_area | 2
sys_r_unit_group
4 | Transaksi | sys_t_access_log | 1
5 | Relasi | sys_x_app_privilege | 4
sys_x_func_privilege
sys_x_unit_privilege
sys_x_user_role
15
2. Daftar Tabel Modul Common
No. | Jenis | Nama | Jumlah
1 | Master | cmn_m_company | 6
cmn_m_ex_person
cmn_m_in_person
cmn_m_location
cmn_m_org_stucture
cmn_m_vehicle_list
2 | Detail | cmn_d_driver_operator | 1
3 | Referensi | cmn_r_parameter | 2
cmn_r_vehicle_type
9
3. Daftar Tabel Modul Eksplorasi
No. | Jenis | Nama | Jumlah
1 | Master | eks_m_drilling | 1
2 | Detail | eks_d_drilling_dtl | 1
3 | Referensi | eks_r_parameter_eksplorasi | 1
4 | Transaksi | eks_t_drilling_hole_reconcile | 3
eks_t_geodas_lithology
eks_t_sample_analysis
6
4. Daftar Tabel Modul Logistik
No. | Jenis | Nama | Jumlah
1 | Master | log_m_part | 3
log_m_part_group
log_m_storage
2 | Header | log_h_part_order | 2
log_h_part_request
3 | Transaksi | log_t_daily_stock | 5
log_t_fuel_compsution
log_t_part_order_dtl
log_t_part_request_dtl
log_t_fuel_tanker
4 | Relasi | log_x_part_location | 1
11
5. Daftar Tabel Modul Produksi
No. | Jenis | Nama | Jumlah
1 | Master | pro_m_crusher | 2
pro_m_dump_rotation
2 | Transaksi | pro_t__record_crusher | 4
pro_t_dump_rotation_veh
pro_t_dump_truck_hauling
pro_t_time_sheet_equipment
6
| Jumlah semua tabel: | 47

## Fungsi
Daftar Fungsi dari Proyek online voting system
Daftar Fungsi Yang harus direalisasi
Proyek : online voting system
Application Name :
1 | Registrasi
2 | Login
3 | Melihat Pilihan
4 | Melakukan voting
5 | Mengirim Email
6 | Mencetak Hasil Voting
No. | Code Fungsi | Designed * |  |  |  |  | Coding |  |  |  |  | Tested |  |  |  |  | Accepted
|  | Due Date | End Date | By PIC |  | Status | Due Date | End Date | By PIC |  | Status | Due Date | End Date | By PIC |  | Status | Due Date | End Date | By PIC |  | Status
|  |  |  | Plan | Real |  |  |  | Plan | Real |  |  |  | Plan | Real |  |  |  | Plan | Real |  | Name
1 | FA-RGS-01 | 2010-04-29 | 1 Mei 2020 | hotma,artha | artha | Closed | 2020-05-04 | 2020-05-06 | Alfredo,Daud | alfredo | Closed | 2020-05-06 | 2020-05-10 | Henny | Alfredo | Closed | [5 empty] | Alfredo
2 | FA-LGN-02 | 2010-04-29 | 1 Mei 2020 |  | artha | Closed | 2020-05-06 | 2018-05-08 |  | aprilia | Closed | 2020-05-08 | 2020-05-10 | Aprilia | Aprilia | Closed | [5 empty] | Aprilia
3 | FA-PLH-03 | 2010-04-29 | 1 Mei 2020 |  | hotma | Closed | 2020-05-08 | 2020-05-13 |  | hotma | Closed | 2020-05-13 | 2020-05-16 | Henny | Hotma | Closed | [5 empty] | Artha
4 | FA-VTN-04 | 2010-04-29 | 1 Mei 2020 |  | artha | Closed | 2020-05-13 | 2020-05-22 |  | henny | Closed | 2020-05-21 | 2020-05-25 | Aprilia | Artha | Closed | [5 empty] | Daud
5 | FA-SND-05 | 2010-04-29 | 1 Mei 2020 |  | hotma | Closed | 2020-05-15 | 2020-05-22 |  | artha | Closed | 2220-05-20 | 2020-05-26 | Aprilia | Daud | Closed | [5 empty] | Henny
6 | FA-HSL-06 | 2010-04-29 | 1 Mei 2020 |  | hotma | Closed | 2020-05-20 | 2020-06-01 |  | daud | Closed | 2020-05-29 | 2020-06-02 | Henny | Henny | Closed | [5 empty] | Hotma
Status
Open
Closed
Pending
in progress
Dropped

## Form
Perkembangan Pembuatan Form
Daftar Form
Form UI Architect : Kelompok 06
No. | Nama Modul | Nama Tabel | Kode Form | Nama Form | PIC | Tgl Awal | Tgl Akhir | Status | Name | Status
1 | Registrasi | t_user | FO-RGS-01 | Form Add Nama Lengkap | Kelompok 06 | 4 Mei 2020 | 6 Mei 2020 | Closed | Kelompok 06 | Open
|  |  | FO-RGS-02 | Form Add Email |  | 4 Mei 2020 | 6 Mei 2020 | Closed |  | In Progress
|  |  | FO-RGS-03 | Form Add Username |  | 4 Mei 2020 | 6 Mei 2020 | Closed |  | Closed
|  |  | FO-RGS-04 | Form Add Password |  | 4 Mei 2020 | 6 Mei 2020 | Closed |  | Dropped
2 | Login | t_user | FO-LGN-01 | Form Add Username |  | 6 Mei 2020 | 8 Mei 2020 | Closed |  | Pending
|  |  | FO-LGN-02 | Form Add Password |  | 6 Mei 2020 | 8 Mei 2020 | Closed
3 | Melihat Pilihan | t_kandidat | FO-VW-01 | Form View Kandidat |  | 8 Mei 2020 | 13 Mei 2020 | Closed
4 | Melakukan Voting | m_voting | FO-VOT-01 | Form Voting |  | 13 Mei 2020 | 22 Mei 2020 | Closed
5 | Mengirim Email | hasil_voting | FO-EML-01 | Form Send Email |  | 15 Mei 2020 | 22 Mei 2020 | Closed
6 | Mencetak Hasil Voting | hasil_voting | FO-HSL-01 | Form Hasil Voting |  | 20 Mei 2020 | 1 Juni 2020 | Closed

## Plan VS Act (hidden)
| Planning |  |  |  |  | Actual
Time | MP | Target | Achieve | Plan Achieve | Total Target | MP | Act. Target | Act. Achieve | Act. Pending | Target
W1 Juni | 4 | 8 | 8 | 8 | 132 | 6 | 18 | 12 | 6 | 132
W2 Juni | 4 | 8 | 16 | 16 | 132 | 5 | 28 | 23 | 5 | 132
W3 Oct | 4 | 8 | 24 | 24 | 132 | 4 | 34 | 31 | 3 | 132
W4 Oct | 4 | 8 | 32 | 32 | 132 | 6 | 45 | 34 | 11 | 132
W3 Nov | 6 | 12 | 44 | 44 | 132 | 8 |  |  |  | 132
W4 Nov | 6 | 12 | 56 | 56 | 132 |  |  |  |  | 132
W1 Dec | 6 | 12 | 68 | 68 | 132 |  |  |  |  | 132
W2 Dec | 6 | 12 | 80 | 80 | 132 |  |  |  |  | 132
W3 Dec | 9 | 16 | 96 | 96 | 132 |  |  |  |  | 132
W4 Dec | 9 | 16 | 112 | 112 | 132 |  |  |  |  | 132
W1 Jan | 9 | 18 | 130 | 130 | 132 |  |  |  |  | 132
W2 Jan | 9 | 18 | 148 | 148 | 132 |  |  |  |  | 132
W3 Jan | 9 | 18 | 166 | 166 | 132 |  |  |  |  | 132
W4 Jan | 9 | 18 | 184 | 184 | 132 |  |  |  |  | 132
W1 Feb | 9 | 16 | 200 | 200 | 132 |  |  |  |  | 132

## Tabel-Fungsi
Hasil Mapping Antara Tabel dan Fungsi
No. | Nama Fungsi | Nama Tabel | Kode Fungsi | Nama Fungsi
1 | Registrasi | t_user | FA-RGS-01 | Fungsi Registrasi
2 | Login | t_user | FA-LGN-02 | Fungsi Login
3 | Melihat Pilihan | t_kandidat | FA-PLH-03 | Fungsi Melihat Pilihan
4 | Melakukan Voting | m_voting | FA-VTN-04 | Fungsi Melakukan Voting
5 | Mengirim Email | hasil_voting | FA-SND-05 | Fungsi Mengirim Email
6 | Mencetak Hasil Vote | hasil_voting | FA-HSL-06 | Fungsi Mencetak hasil vote

## Programmer
Period | PIC | Week Target | Week Achieve | Pending | Total Target | Total Achieve | Total Pending
Week 13-14 | Henny | 100% | 90% | 10% | 100% | 85% | 0 | Desain user interface, mock up, dan proses bisnis
| Artha | 100% | 85% | 15% | 100% | 85% | 0
| Hotma | 100% | 85% | 15% | 100% | 85% | 0
| Aprilia | 100% | 85% | 15% | 100% | 85% | 0
| Daud | 100% | 85% | 15% | 100% | 85% | 0
| Alfredo | 100% | 85% | 15% | 100% | 85% | 0
Week 14-15 | Henny | 100% | 80% | 20% | 100% | 80% | 20% | Implementasi User Interface dan Main Function
| Artha | 100% | 75% | 25% | 100% | 75% | 40%
| Hotma | 100% | 75% | 25% | 100% | 75% | 30%
| Aprilia | 100% | 50% | 40% | 100% | 50% | 40%
| Daud | 100% | 60% | 40% | 100% | 60% | 40%
| Alfredo | 100% | 50% | 30% | 100% | 50% | 30%
Week 15-16 | Henny | 100% | 100% | 0 | 100% | 100% | 0 | Implementasi Main Function dan Testing produk
| Artha | 100% | 100% | 0 | 100% | 100% | 0
| Hotma | 100% | 100% | 0 | 100% | 100% | 0
| Aprilia | 100% | 100% | 0 | 100% | 100% | 0
| Daud | 100% | 100% | 0 | 100% | 100% | 0
| Alfredo | 100% | 100% | 0 | 100% | 100% | 0

## Data Entry (hidden)
Daftar Tabel |  | Total Tabel | Master | 17
Data Architect : ??? |  |  | Referensi | 5
DBA : ??? |  |  | Transaksi | 13
|  |  | Header | 2
|  |  | Detail | 5
|  |  | Relasi | 5
47
No | Modul | Nama | Jenis | PIC | Status
[5 empty] | Designed * |  | Created |  | Modified | Jlh. Rec | Pemeriksa | Data Entry
[5 empty] | Plan | Real | Plan | Real | (last) |  |  | Tgl Mulai | Tgl Akhir | Status | Name | Status
1 | Framewok SIDEL (sys) | sys_m_application | Master |  | - | - | 2011-06-20 | 2011-06-20 | - | [5 empty] | Mayer | Open
|  | sys_m_imap | Master |  | - | - | 2011-06-20 | 2011-06-20 | - | [5 empty] | Whidia | In Progress
|  | sys_m_role | Master |  | - | - | 2011-06-20 | 2011-06-20 | 2011-07-04 | [5 empty] | Alex Sandro | Closed
|  | sys_m_table | Master |  | - | - | 2011-06-20 | 2011-06-20 | - | [5 empty] | Fitriani | Dropped
|  | sys_m_user | Master |  | - | - | 2011-06-20 | 2011-06-20 | 2011-07-04 | [5 empty] | Togu | Pending
|  | sys_d_function | Detail |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_d_profile | Detail |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_d_unit | Detail |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_r_area | Referensi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_r_unit_group | Referensi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_t_access_log | Transaksi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_x_app_privilege | Relasi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_x_func_privilege | Relasi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_x_unit_privilege | Relasi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_x_user_role | Relasi |  | - | - | 2011-06-20 | 2011-06-20 | 2011-07-04
1 | Common | cmn_m_company | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  |  |  | 2011-07-15 |  | In Progress | Angripa | Open
|  | cmn_m_ex_person | Master | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 126 | Tobby | 2011-07-19 | 2011-07-21 | Closed | Tobby | In Progress
|  | cmn_m_in_person | Master | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 120 | Tobby | 2011-07-19 | 2011-07-20 | Closed | Mayer | Closed
|  | cmn_m_location | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | 2011-07-07 |  |  | 2011-07-15 |  | In Progress | Whidia | Dropped
|  | cmn_m_org_stucture | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 37 | Angripa |  |  |  |  | Pending
|  | cmn_m_vehicle_list | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | cmn_d_driver_operator | Detail | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | cmn_r_parameter | Referensi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 365 | Tobby | 2011-07-15 | 2011-07-21 | Closed
|  | cmn_r_vehicle_type | Referensi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  |  |  | 2011-07-15 |  | In Progress
2 | Eksplorasi | eks_m_drilling | Master | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 287 | Tobby | 2011-07-04 | 2011-07-22 | In Progress
|  | eks_d_drilling_dtl | Detail | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 447 | Tobby | 2011-07-08 | 2011-07-22 | In Progress
|  | eks_r_parameter_eksplorasi | Referensi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  |  |  | 2011-07-15 |  | In Progress
|  | eks_t_drilling_hole_reconcile | Transaksi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Open
|  | eks_t_geodas_lithology | Transaksi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Open
|  | eks_t_sample_analysis | Transaksi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Open
3 | Logistik | log_m_part | Master |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_m_part_group | Master |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_m_storage | Master |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | 2011-07-07
|  | log_h_part_order | Header |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_h_part_request | Header |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_part_order_dtl | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_part_request_dtl | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_daily_stock | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_fuel_compsution | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_fuel_tanker | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_x_part_location | Relasi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
4 | Produksi | pro_m_crusher | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Closed
|  | pro_m_dump_rotation | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 201 | Angripa | 2011-07-04 | 2011-07-19 | Closed
|  | pro_t__record_crusher | Transaksi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Closed
|  | pro_t_dump_rotation_veh | Transaksi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 600 | Angripa | 2011-07-05 | 2011-07-19 | Closed
|  | pro_t_dump_truck_hauling | Transaksi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Closed
|  | pro_t_time_sheet_equipment | Transaksi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Closed